# CHAPTER 74-1

# AGENCY FOR STATE TECHNOLOGY PROJECT MANAGEMENT AND OVERSIGHT

# 74-1.001	Purpose and Applicability; Definitions

# 74-1.002	Risk and Complexity Assessment

# 74-1.003	Initiation

# 74-1.004	Planning

# 74-1.005	Execution

# 74-1.006	Monitoring and Controlling

# 74-1.007	Closeout

# 74-1.008	Compliance with the Florida Information Technology Project Management and Oversight Standards

# 74-1.009	Agency for State Technology (AST) Oversight

## 74-1.001 Purpose and Applicability; Definitions.

(1) Purpose and Applicability.

(a) Rules 74-1.001 through 74-1.009, F.A.C., will be known as the Florida Information Technology Project Management and Oversight Standards. These rules include two separate sets of requirements ‒ project management standards defined in rules 74-1.001 through 74-1.008, F.A.C., and Agency for State Technology (AST) project oversight requirements defined in rule 74-1.009, F.A.C.

(b) This rule establishes project management standards when implementing information technology (IT) projects. State Agencies must comply with these standards when implementing all IT projects. Cabinet Agencies must comply with these standards when implementing IT projects that have a total cost of $25 million or more and that impact one or more other agencies (pursuant to section 282.0051(15)(a), F.S.). For all other IT projects, Cabinet Agencies are required to either adopt these standards or adopt alternative standards based on best practices and industry standards (See section 282.00515, F.S.). These standards are documented in rule 74-1.001 through 74-1.008, F.A.C.

1. Operations and Maintenance (O&M) activities that support an existing product or service to keep it in conformance with its originally intended specifications, functionality, and service levels are exempt from these standards. O& M activities include:

a. Adaptive Maintenance ‒ the modification of a product, performed after delivery, to keep a product usable in a changed or changing environment.

b. Corrective Maintenance ‒ the reactive modification of a product performed after delivery to correct discovered problems.

c. Perfective Maintenance ‒ the modification of a product after delivery to detect and correct latent faults in the product before they are manifested as failures.

d. Preventive Maintenance ‒ the modification of a product after delivery to detect and correct latent faults in the product before they become operational faults.

The terms above originate from the International Organization for Standardization standard No.: ISO/IEC 14764:2006, which may be found at: https://www.iso.org/obp/ui#iso:std:iso-iec-ieee:24765:ed-1:v1:en.

O&M activities include, but are not limited to, break-fix actions, routine software upgrades, and network component replacements.

2. These standards, per section 282.0051(3), F.S., also address:

a. Performance measurements and metrics that objectively reflect the status of an IT project based on a defined and documented project schedule, cost, and scope.

b. Methodologies for calculating acceptable variances in the projected versus actual schedule, cost, and scope of an IT project.

c. Reporting requirements, including requirements designed to alert all defined stakeholders that an IT project has exceeded acceptable variances.

d. Content, format, and frequency of project updates.

3. In 2016, AST will begin conducting annual assessments to determine State Agency compliance with the Florida Information Technology Project Management and Oversight Standards set forth in rule 74-1.008, F.A.C. (Per section 282.0051(10), F.S.)

4. State Agencies, and as applicable Cabinet Agencies, will use the Florida Information Technology Project Management and Oversight Standards set forth in this rule in competitive solicitations and procurement documents or contract agreements for IT projects, as appropriate, to provide project management standards for potential vendors.

(c) This rule establishes oversight standards that the Agency for State Technology (AST) will use for oversight of IT projects. These standards apply to IT projects of State Agencies that have a total cost of $10 million or more and that are funded in the General Appropriations Act or any other law; and IT projects of Cabinet Agencies with a total cost of $25 million or more and that impact one or more other agencies. (Per sections 282.0051(4), and 282.0051(15)(a), (b), F.S.). These standards are documented in rule 74-1.009, F.A.C.

(2) Definitions.

(a) The following terms are defined:

1. Action Item ‒ A documented event, task, activity, or action that needs to take place. Action Items are discrete units that are assigned to a single person for tracking and reporting until resolution.

2. Agency(ies) ‒ For purposes of this rule, Agency(ies) means State Agencies, and Cabinet Agencies when implementing IT projects that have a total project cost of $25 million or more and that impact one or more other Agencies.

3. Alternative Analysis – A technique used to evaluate identified options in order to select which options or approaches to use to execute and perform the work of the project. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013. The PMBOK Guide, 5th Edition, is incorporated by reference into this rule.

4. AST – Agency for State Technology.

5. Baseline – The approved version of a work product that can be changed only through formal change control procedures and is used as a basis for comparison. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

6. Baselined Schedule ‒ The agency-approved version of the project schedule that can be changed only through formal change control procedures. This document is used as a basis for Earned Value Analysis.

7. Business Case – Describes the necessary information from a business standpoint to determine whether or not the project is worth the required investment.

8. Cabinet Agency(ies) – The Department of Legal Affairs, the Department of Agriculture and Consumer Services, and the Department of Financial Services.

9. Change Control – A process whereby modifications to project documents, deliverables, or baselines are identified, documented, reviewed, and approved, or rejected. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

10. Complexity – Technological and management characteristics of the project and the potential impacts, both positive and negative, that these characteristics could have on the project’s risks.

11. Corrective Action – An intentional activity that realigns the performance of the project work with the project management plan. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

12. Corrective Action Plan ‒ A plan that illustrates corrective actions required to bring the project back within established schedule, cost, and scope parameters.

13. Cost Benefit Analysis – A financial analysis tool used to determine the benefits provided by a project against its costs. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

14. Cost Performance Index (CPI) – A measure of the cost efficiency of budgeted resources expressed as the ratio of earned value to actual cost. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

15. Earned Value – The measure of work performed expressed in terms of the budget authorized for that work. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

16. Earned Value Analysis ‒ An approach to measuring project performance that is based on comparing actual progress against planned progress.

17. Independent Verification and Validation (IV&V) – A review of the project plans and other project artifacts by an independent third party. The primary objective of an IV&V is to provide an objective assessment of products and processes throughout the project management lifecycle. In addition, IV&V will facilitate early detection and correction of issues, enhance management insight into risks, and ensure compliance with project performance, schedule, and budget requirements. The IV&V entity must have no technical, managerial, or financial interest in the project and will not have any responsibility for, or participation in, any other aspect of the project.

18. Information Technology – Equipment, hardware, software, firmware, programs, systems, networks, infrastructure, media, and related material used to automatically, electronically, and wirelessly collect, receive, access, transmit, display, store, record, retrieve, analyze, evaluate, process, classify, manipulate, manage, assimilate, control, communicate, exchange, convert, converge, interface, switch, or disseminate information of any kind or form as defined in section 282.0041(11), F.S.

19. Issue ‒ A point or matter in question or in dispute, or a point or matter that is not settled and is under discussion or over which there are opposing views or disagreements. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013. An issue must be resolved as soon as possible; otherwise, it will have detrimental effects on the project.

20. PMP® Certified Project Manager – Project Management Professional (PMP®) is a certification administered by the Project Management Institute that demonstrates experience, education, and competency to lead and direct projects.

21. Project ‒ An endeavor that has a defined start and end point; is undertaken to create or modify a unique product, service, or result; and has specific objectives that, when attained, signify completion as defined in section 282.0041(16), F.S.

22. Project Change ‒ Something that is outside the documented and approved project scope or is a change to baselined project requirements, project schedule, or project cost (including resource effort). A project change requires approval, by project governance, for additional resources, funding, or modifications to the project schedule.

23. Project Governance – The alignment of project objectives with the strategy of the larger organization by the project sponsor and project team. A project’s governance is defined by and is required to fit within the larger context of the program or organization sponsoring it, but is separate from organizational governance. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013. Project governance is an oversight process aligned with (but separate from) the Agency management structure. Project governance provides the project manager, project team, project sponsor(s), and all stakeholders with structure, processes, decision-making models, and tools to ensure the successful management of the project and delivery of the product. It includes a framework for making project decisions (including project change control and deliverable acceptance) and defining roles, responsibilities, and accountabilities for the success of the project.

24. Project Life Cycle (PLC) – The project life cycle encompasses all the project management activities of the project grouped by the standard PLC phases of Initiation, Planning, Monitoring and Controlling, Execution, and Closure.

25. Project Oversight – Independent review and analysis of an information technology project that provides information on the project’s scope, completion timeframes, and budget and that identifies and quantifies issues or risks affecting the successful and timely completion of the project as defined in section 282.0041(17), F.S.

26. Project Management Plan or Project Plan ‒ The document that describes how the project will be executed, monitored, and controlled. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

27. Project Schedule – A listing of a project's milestones, activities, and deliverables, with work estimates and start and finish dates. These estimates include budget and resource allocation, as well as task sequencing and dependencies.

28. Project Sponsor ‒ The State Agency senior management role that approves the allocation of resources for an endeavor, develops a common vision, provides ongoing commitment to the project, and continually assesses success.

29. Project Variance ‒ A quantifiable or qualitative deviation from an approved baseline or expected value. AST will use Cost Performance Index (CPI) and Schedule Performance Index (SPI) calculations and budget and scope variance analysis to determine the degree of project variance between project baselines and actual project performance.

30. Risk – An uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

31. Risk Manager – An individual responsible for managing a project’s risk, such as conducting risk management planning, risk identification, analysis, response planning, and tracking of risks and mitigation throughout the project.

32. Schedule Performance Index (SPI) – A measure of schedule efficiency expressed as the ratio of earned value to planned value. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013.

33. Scope Baseline – Documented scope and objectives set forth in the agency-approved project plan document.

34. Scope Variance ‒ Deviation from the documented objectives and scope set forth in the agency-approved project plan documents.

35. Scope Variance Analysis ‒ An approach to measuring project performance that is based on comparing actual scope against planned scope.

36. Significant Change ‒ Significant Change are those changes that will modify a project’s approved cost, schedule, or scope, either by themselves or cumulatively, by more than 10%.

37. Stakeholder – A person, group, organization, or state agency involved in or affected by a course of action as defined in Section 282.0041(21), F.S.

38. State Agency(ies) ‒ Any official, officer, commission, board, authority, council, committee, or department of the executive branch of state government; the Justice Administrative Commission; and the Public Service Commission. The term does not include university boards of trustees or state universities. The term does not include the Department of Legal Affairs, the Department of Agriculture and Consumer Services, or the Department of Financial Services as defined in section 282.0041(23), F.S. (See Cabinet Agency(ies))

39. Trend – a series of at least three data points indicating movement upward or downward.

40. Variance – a calculated value that illustrates how far (positive or negative) a projection has deviated when measured against documented estimates within a project plan as defined in section 282.0041(27), F.S.

41. Work Breakdown Structure (WBS) ‒ A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, PA: Project Management Institute, 2013. The WBS is a framework for overall planning and is the basis for dividing work into definable increments from which schedule, cost, and scope can be defined.

42. Work Package – The work defined at the lowest level of the work breakdown structure for which cost and duration can be estimated and managed. Definition from: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 5th Edition. Newtown Square, Pa: Project Management Institute, 2013.

(b) A copy of the PMBOK Guide may be obtained from the Project Management Institute, 14 Campus Boulevard, Newtown Square, Pennsylvania 29073-3299, or www.pmi.org.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.00515 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.002 Risk and Complexity Assessment.

(1) The Agency will perform Risk & Complexity Assessments (R&C Assessments) for information technology (IT) projects to evaluate the risk and complexity factors for each IT project https://www.flrules.org/Gateway/reference.asp?No=Ref-05569. The purpose of the assessments is to determine the minimum level of project management control necessary to manage a given project in order to reduce risk and increase the probability of success.

(2) These assessments align projects by risk and complexity levels into one (1) of four (4) Risk and Complexity (R&C) Categories, which determine the amount of project management control required. The following diagram indicates the distribution of risk and complexity levels into the R&C Category:

|  | Complexity |
| --- | --- |
|  | Low | Medium | High |
| Risk | Low | 1 | 1 | 2 |
|  | Medium | 2 | 2 | 3 |
|  | High | 3 | 3 | 4 |

(a) Category 4 represents High Risk and High Complexity projects.

(b) Category 3 represents High Risk and Medium Complexity projects, High Risk and Low Complexity projects, or Medium Risk and High Complexity projects.

(c) Category 2 represents Medium Risk and Medium Complexity projects, Medium Risk and Low Complexity projects, or Low Risk and High Complexity projects.

(d) Category 1 represents Low Risk and Medium Complexity projects or Low Risk and Low Complexity projects.

(e) Specific lifecycle phase requirements for each category are identified in rule 74-1.003, F.A.C. ‒ Initiation; rule 74-1.004, F.A.C. ‒ Planning; rule 74-1.005, F.A.C. ‒ Execution; rule 74-1.006, F.A.C. ‒ Monitoring and Controlling; and rule 74-1.007, F.A.C. ‒ Closure.

(3) The R&C Assessments are conducted using Form AST-F-0505A, AST Risk & Complexity Assessment Workbook (07/15). This workbook is used by Agencies to determine the cumulative R&C Category designation. The R&C Assessment Workbook is divided into seven (7) separate assessment worksheets which are conducted at four (4) key points in the project management life cycle. Form AST-F-0505A, AST Risk & Complexity Assessment Workbook, is hereby incorporated by reference in this Rule. Form AST-F-0505A can be found on the AST website at: http://www.ast.myflorida.com/.

(a) The Agency must complete a Pre-Charter R&C Assessment (consisting of a Risk worksheet and a Complexity worksheet) at the start of the Initiation phase of the project. During this assessment, the Agency will review priorities and business need, assess the project, and analyze factors that might impact project success. The resulting R&C Category establishes the project management control requirements to be applied during the project Initiation phase. (See rule 74-1.003, F.A.C. ‒ Initiation)

(b) The Agency must complete an Initiation Gate R&C Assessment at the end of the Initiation phase following completion of project Initation documentation. During this assessment, the Agency will review Initiation documents, validate or amend the previous R&C assessment findings, and complete the Initiation Gate R&C Assessment (consisting of a Risk worksheet and a Complexity worksheet). This assessment will confirm or adjust the project’s cumulative risk & complexity level and resulting R&C Category, examine the effectiveness of Initiation phase activities, and set requirements for the project Planning phase. (See rule 74-1.004, F.A.C. ‒ Planning)

(c) The Agency must complete a Planning Gate R&C Assessment at the end of the Planning phase, following completion of project planning documentation. During this assessment, the Agency will review project documents, validate or amend the previous R&C assessment findings, and complete the Planning Gate R&C Assessment (consisting of a Risk worksheet and a Complexity worksheet). This assessment will confirm or adjust the project’s cumulative risk and complexity level and resulting R&C Category, examine the effectiveness of Planning phase activities, and set requirements for the project Execution and Monitoring and Controlling phases. (See rule 74-1.005, F.A.C. ‒ Execution, and rule 74-1.006, F.A.C. ‒Monitoring and Controlling)

(d) The Agency must complete an Event-Driven R&C Assessment if the project experiences a significant change, or cumulative changes (in cost, schedule, or scope) from the project baseline. During this assessment, the Agency will review the change control request(s) and project documentation. The Agency will also review, validate or amend the previous R&C assessment findings, and complete the Event-Driven R&C Assessment (consisting of a Risk worksheet). This assessment will confirm or adjust the project’s cumulative risk & complexity level and resulting R&C Category and determine if review and amendment to project management baselines are needed.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.

## 74-1.003 Initiation.

(1) Project Initiation is the first phase in the project management lifecycle. In the Initiation phase, information technology projects are transitioned from ideas to a viable project proposal (through the Agency’s project request process) for consideration and approval by the Agency’s management.

(2) The Agency must complete the Pre-Charter Risk and Complexity (R&C) Assessment for the project (see rule 74-1.002 ‒ Risk and Complexity Assessment, F.A.C.). This assessment will provide the project risk and complexity levels and resulting R&C Category, which will define the management control activities required for the Initiation phase.

(3) The following matrix lists Initation phase activities and documents required for the project based on its R&C Category.

(4) Specific document types, templates, or formats are not prescribed – any documentation that contains the information specified in the requirements below is acceptable.

| INITIATION PHASE ‒ Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Pre-Charter Risk and Complexity (R&C) Assessment | Required |
|  | 4 | 3 | 2 | 1 |
| Business Case and Alternative Analysis | Required – Articulate a clear path to a return on investment (ROI) or business value in instances where a positive ROI is not present. Demonstrate a clear understanding of the processes, costs, strengths, and weaknesses of the Agency’s current business process. Document, identify, and analyze potential solutions. Provide a compelling argument for implementation and examine benefits and risks associated with the recommended course of action as well as not taking the action. | Required ‒ Provide a brief justification for the project in the Project Charter by answering the questions: Why is the project necessary? What problem is being solved? |
|  | 4 | 3 | 2 | 1 |
| Cost Benefit Analysis | Required ‒ Document the economic feasibility of the alternatives being considered including the planned project costs, as well as each of the tangible benefits, and then calculate key financial performance metrics such as ROI and payback period. | Required ‒ Include a brief discussion of any cost savings or cost avoidance expected, if applicable, in the Project Charter. |
|  | 4 | 3 | 2 | 1 |
| Project Charter | Required ‒ Document the project description and high level objectives; scope/out of scope; initial estimates for budget, duration, and work effort; assumptions/constraints; and initial risks. Identify the project manager, stakeholders and anticipated project resources. |
|  | 4 | 3 | 2 | 1 |
| Centralized Project Repository | Required ‒ Establish a centralized project repository to house and archive all project documentation. |
|  | 4 | 3 | 2 | 1 |
| PMP® Certified Project Manager | Required ‒ The Project Manager must be PMP® certified. The PMP® Certified Project Manager is authorized by the Agency to lead the entire project team in the completion of the full project scope throughout the project lifecycle. This project manager must be an Agency employee or contractor (individual) of the Agency. | Not Required |
|  | 4 | 3 | 2 | 1 |
| Risk Manager | Recommended ‒ Appointment of a Risk Manager, other than the Project Manager. | Not Required |
|  | 4 | 3 | 2 | 1 |
| Independent Verification and Validation (IV&V) | Recommended ‒ Employ Independent Verification and Validation (IV&V). | Not Required |

|  | 4 | 3 | 2 | 1 |
| --- | --- | --- | --- | --- |
| Initiation Gate R&C Assessment | Required |

(5) The Agency must complete the Initiation Gate R&C Assessment (see rule 74-1.002, F.A.C. ‒ Risk and Complexity Assessment). This Assessment will confirm or adjust the project’s risk and complexity levels and the resulting R&C Category, validate Initiation management control requirements, and set management control requirements for the subsequent Planning phase.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.004 Planning.

(1) In the Planning phase, the Agency develops and approves detailed project planning documents.

(2) The matrix provided below lists planning activities and documents required for the project based on the project’s Risk and Complexity (R&C) Category.

(a) Specific document types, templates, or formats are not prescribed – any documentation that contains the information specified in the requirements below is acceptable.

(b) This documentation, whether created separately or combined as a single document, constitutes the Project Management Plan.

| PLANNING PHASE ‒ Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Project Scope | Required ‒ Clearly delineate the project scope, specifically what is in scope, what is out of scope, project objectives, and deliverables. This will determine scope baselines and variances. Discuss how the project scope and objectives trace back through the Project Charter to initial project documents such as the Schedule IV-B. Document the approach for project execution (identify the Software Development Life Cycle model that will be used – such as Agile, waterfall, etc.) Identify assumptions and constraints. | Required ‒ Summarize the project scope (in scope and out of scope). |
|  | 4 | 3 | 2 | 1 |
| Work Breakdown Structure (WBS) | Required – Document the hierarchical and incremental decomposition of the project into phases, deliverables, and work packages. Identifies all the tasks required to deliver the total project scope of work to produce each deliverable. Tasks must be decomposed into subtasks until they can be estimated, observed, and evaluated. | Not Required |
|  | 4 | 3 | 2 | 1 |
| Project Organizational and Governance Structure | Required – Document a representation of the project from an organizational perspective. Include an organization chart with stakeholder and governance structures identified. Include a detailed description of the project and the Agency’s governance process with roles, responsibilities, and approval authorities identified for project documents or artifacts, including any processes for final product acceptance. Include reporting and escalation parameters for variances in baseline schedule, cost, and scope. | Required ‒ Identify the project stakeholders and the responsibilities for decision-making and escalation. |
|  | 4 | 3 | 2 | 1 |
| Resource Plan | Required ‒ Document the resources required to complete the project and how these resources will be acquired. For human resources – identify project roles, skills, number, and resource type required, and specify the method(s) for acquiring new personnel or incorporating and backfilling the current responsibilities of existing personnel. For equipment or materials ‒ identify types, quantities, and purpose, and specify the method(s) for acquiring equipment or materials. | Recommended: List the number and type of resources anticipated and what, if any, resources must be procured. |
|  | 4 | 3 | 2 | 1 |
| Schedule Management Plan | Required ‒ Document the approach to create an integrated master schedule that encompasses the total scope of the project and identifies the projects critical path. Describe the process for establishing and changing the schedule baseline. Describe the responsibilities, timeframes, and methods to manage, update and report progress (including Earned Value Analysis) throughout the project. | Recommended ‒ Document the approach to create an integrated master schedule that encompasses the total scope of the project and identifies the projects critical path. |
|  | 4 | 3 | 2 | 1 |
| Project Schedule | Required ‒ Develop and maintain an integrated master project schedule that identifies the total project scope of work (including milestones and deliverables); is task, resource, and cost loaded; identifies the project critical path, is baselined and updated with project progress; and contains the information necessary to provide earned value analysis and support schedule and cost performance index (SPI and CPI) variance analysis and reporting. | Required ‒ Develop, and maintain a schedule that identifies the total project scope of work, assigned resources, and task start and end dates. |
|  | 4 | 3 | 2 | 1 |
| Project Budget | Required ‒ Develop and maintain a Project Budget, which must include specific fiscal year cost totals over the life of the project and the overall total cost of the project. Also include a description of the funding source(s) for the Project and a breakdown of the Project costs by major expense categories. | Required – Develop and maintain a Project Budget, which must include specific fiscal year cost totals over the life of the project and the overall total cost of the project. |
|  | 4 | 3 | 2 | 1 |
| Project Spending Plan | Required ‒ Develop and maintain a Project Spending Plan, which, as a component of the Project Budget, must include monthly planned (baselined) and actual expenditures (by expenditure or expenditure category) for each fiscal year. | Required ‒ Document current fiscal year planned expenditures and actual expenditures by month and Fiscal Year total to date. Include other expenditure detail as required for the Project Status Report. | Recommended ‒ Document current fiscal year planned expenditures and actual expenditures by month and Fiscal Year total to date. |
|  | 4 | 3 | 2 | 1 |
| Communications Management Plan | Required ‒ Identify the project information requirements of stakeholders and detail what, when, and how information will be collected and reported. This will include the responsibility, frequency, format, and distribution method for meeting summaries, project status reports, project governance meetings, and stakeholder communications, including reporting variances in schedule, cost, or scope and emerging risks or issues. Document the location of the project repository. Include documentation for Decision Tracking and Action Item Tracking (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). | Required ‒ Identify the project information requirements of stakeholders and detail what, when, and how information will be collected and reported. |
|  | 4 | 3 | 2 | 1 |
| Change Management Plan | Required ‒ Document the change control process and documentation involved in identifying, analyzing impacts, escalating, approving, and managing project change requests related to the project’s schedule, cost, or scope baselines, or a change to project deliverables (see rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). |
|  | 4 | 3 | 2 | 1 |
| Quality Management Plan | Required ‒ Document the processes and procedures for ensuring quality planning, quality assurance, and quality control are all conducted. | Required ‒ Document any method(s) for ensuring customer acceptance of the product or service. |
|  | 4 | 3 | 2 | 1 |
| Deliverable Acceptance Plan | Required ‒ Document each deliverable, the acceptance criteria for each deliverable, and the deliverable acceptance process (including roles and responsibilities). | Required ‒ List the deliverables and the person(s) responsible for approving deliverables. |
|  | 4 | 3 | 2 | 1 |
| Risk Management Plan | Required ‒ Document the process for the descriptive identification (listing), evaluation (probability and impact), prioritization, and response to risks (specified mitigation strategies for each risk), as well as the nature of any time sensitivity to risks that may impact the project. Identify the roles and responsibilities of individuals assigned to risks. Identify and document the process to be used for tracking, periodic review, and update of Risks (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). | Required ‒ Describe the method for monitoring and controlling risk. |
|  | 4 | 3 | 2 | 1 |
| Issue Management Plan | Required ‒ Document the process for (and the documentation of) the identification, evaluation, management, and resolution to issues impacting the project. Identify and document the process to be used for tracking, periodic review, and update of Issues (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). Identify the roles and responsibilities of project staff. | Required ‒ Describe the method for monitoring and addressing issues. |
|  | 4 | 3 | 2 | 1 |
| Procurement Management Plan | Required ‒ If procurement is required by the project, document any products or services needed, identify the specific products and services to be purchased, along with the appropriate purchasing methods, rules, and statutes affecting these activities. | Required ‒ List any procurements required for the project. |
|  | 4 | 3 | 2 | 1 |
| Organizational Change Management Plan | Required ‒ Document the impact of delivering the project’s products to the user organization and individual users; the readiness of the user organization and individual users to accept those changes; and describe and plan the action necessary to facilitate those changes. | Required ‒ Document the impact of delivering the projects products to the user organization and the individual users. | Recommended – Document the impact of delivering the projects products to the user organization and the individual users. |
|  | 4 | 3 | 2 | 1 |
| Florida Cybersecurity Standards | Required – Compliance with Rule Chapter 74-2, F.A.C. |
|  | 4 | 3 | 2 | 1 |
| Requirements Traceability Matrix (RTM) | Required ‒ Prepare a document (usually a table) that links high-level design and requirements with detailed requirements, detailed design, test plan, and test cases. The RTM ensures that all requirements are identified and correctly linked (from high-level to detailed and technical levels) throughout the project. | Required ‒ Document Requirements. |
| Planning Gate R&C Assessment | Required |

(3) The Agency must complete the Planning Gate R&C Assessment at the end of the Planning phase (see rule 74-1.002 ‒ Risk and Complexity Assessment, F.A.C.). This Assessment will confirm or adjust the project’s risk and complexity levels and the resulting R&C Category, validate Planning management control requirements, and set management control requirements for the subsequent Execution and Monitoring and Controlling phases.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.005 Execution.

(1) The Execution phase involves carrying out and managing all the activities described in the Project Management Plan.

(2) The majority of Execution phase activities and documentation will be associated with the Agency’s specific Systems Development Life Cycle (SDLC) process and requirements.

| EXECUTION PHASE ‒ Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Operations and Maintenance (O&M) Plan | Required ‒ Develop an O&M Plan prior to the scheduled completion of the project’s Execution phase. Document concurrence from those responsible for the operation and maintenance (e.g., financial, information technology, and operational managers, etc.) on their readiness to support the system from a budgetary, staffing, technology, and operational perspective after go-live. | Recommended |
|  | 4 | 3 | 2 | 1 |
| Project Management Plans | Required ‒ As necessary, update Project Management Plan documents. |

(4) Agency project management activities required during the Execution phase are further described in rule 74-1.006, F.A.C. ‒ Monitoring and Controlling.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.006 Monitoring and Controlling.

(1) Project Monitoring and Controlling spans all phases of the project and involves the regular review of project status in order to identify variances from baselined project schedule, cost, and scope. In addition, all project management plan components developed pursuant to rule 74-1.004, F.A.C., Planning, must be monitored, controlled and maintained.

(2) Risk and Complexity (R&C) Category 4 and 3 Projects will use Earned Value analysis to ensure that the schedule provides an accurate representation of project status.

(a) Schedule Performance Index (SPI)

1. SPI is a measure of schedule efficiency expressed as a ratio of Earned Value (EV) to Planned Value (PV): SPI = EV/PV, where Earned Value is the measure of work performed expressed in terms of the budget amount authorized for that work, and Planned Value is the authorized budget assigned to scheduled work. Planned Value corresponds to the approved baseline budget.

2. A SPI value of less than 1.0 indicates that less work was completed, in a given time frame, than was planned.

3. A SPI value greater than 1.0 indicates that more work was completed, in a given time frame, than was planned.

(b) Cost Performance Index (CPI)

1. CPI is a measure of cost efficiency of budgeted resources for the work completed. CPI is expressed as a ratio of Earned Value (EV) to Actual Cost (AC): CPI = EV/AC, where Earned Value is the measure of work performed expressed in terms of the budget amount authorized for that work, and Actual Cost is the realized cost incurred for the work performed on an activity or set of activities during a specific time period.

2. A CPI value of less than 1.0 indicates a cost overrun for work completed, in a given time frame.

3. A CPI value greater than 1.0 indicates a cost underrun of performance to date.

(3) The following matrix details specific Monitoring and Controlling documentation and activities required for the project based on the project’s R&C Category.

| MONITORING AND CONTROLLING ‒ Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Change | Required ‒ Follow the change control process(es) documented in the Change Management Plan. Complete an Event-Driven Risk & Complexity (R&C) Assessment for significant change requests (see rule 74-1.002, F.A.C. ‒ Risk and Complexity Assessment). This assessment will confirm or adjust the project’s cumulative risk and complexity levels and R&C Category, and assist the Agency in determining whether changes to any project management plan documents and baselines are needed. Maintain a change tracking log that includes change description, project impact (scope, schedule, and cost), owner, and status. This log is used to track, enter, review, analyze, approve, update, and report on project changes. |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Schedule | Required ‒ Update the schedule at least weekly to reflect actual progress toward completion of scheduled tasks, milestones, and deliverables. | Required ‒ Update the schedule at least biweekly to reflect actual progress toward completion of scheduled tasks, milestones, and deliverables. |
|  | Required ‒ Use SPI to assess schedule variance. If SPI analysis indicates a trend towards a variance equal to or greater than 10% (SPI score ≤ 0.90 or ≥ 1.10), communicate the variance explanation to the project’s key stakeholder(s). | Required ‒ Evaluate the baselined schedule against current progress. 1. Identify overdue tasks and compute the percentage of late tasks related to total tasks to date (Number of Overdue Tasks/Number of Total Tasks). 2. If this analysis indicates a trend towards a variance, equal to or greater than 10%, communicate the variance explanation to the project’s key stakeholders. |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Cost | Required ‒ Monitor project costs monthly to identify both positive and negative variances between planned and actual expenditures. 1. Compare baselined planned expenditures to actual expenditures captured in the spending plan or the budget. 2. Identify the difference in baselined planned and actual expenditures and compute the percentage of cost variance for the period (Cost Variance/Total Planned Cost). 3. If there is a variance (positive or negative) equal to or greater than 10%, communicate the variance explanation to the project’s key stakeholder(s). |
|  | Required ‒ Use CPI to assess cost variance. If the CPI analysis indicates a trend towards a variance equal to or greater than 10% (CPI score ≤ 0.90 or ≥ 1.10), communicate the variance explanation to the project stakeholders. | Not Required |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Scope | Required ‒ Monitor project scope, and manage changes to the original and agreed-upon scope as documented in the approved project planning documents. | Required ‒ Monitor project scope and document changes. |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Quality | Required ‒ Monitor and Control quality as documented in the Quality Management Plan. |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Risks | Required ‒ Monitor and control risks as documented in the approved Risk Management Plan. Perform risk reassessments to identify new risks, reassess current risks, escalate risks to issues, and close outdated risks. Maintain a risk tracking log that includes risk description, owner, response/mitigation strategy, risk probability, impact, priority, status and open/close dates. This log is used to track, enter, review, analyze, update, monitor, and report on risks. | Required – Monitor, document, and address risks. |
|  | 4 | 3 | 2 | 1 |
| Monitor and Control Project Issues | Required ‒ Monitor and control issues as documented in the approved Issue Management Plan. Review issues to identify new issues, reassess current issues, and close resolved issues. Maintain an issue tracking log, which includes Issue description, owner, status, and dates opened, due and closed. This log is used to track, enter, review, analyze, update, monitor, and report on issues. | Required ‒ Monitor, document, and resolve issues. |
|  | 4 | 3 | 2 | 1 |
| Decision Tracking | Required ‒ Maintain a decision tracking log that includes decision description, approval authority, date of entry, due date, actual date of decision, project impact (scope, schedule, and cost), and status. This log is used to track, enter, review, analyze, update, monitor, and report on decisions. | Recommended |
|  | 4 | 3 | 2 | 1 |
| Action Item Tracking | Required ‒ Maintain an action item log that includes Action Item description, owner, dates assigned and due, and status. This log is used to track, enter, review, analyze, update, monitor, and report on action items. | Recommended |
|  | 4 | 3 | 2 | 1 |
| Florida Cybersecurity Standards | Required – Monitor and control project compliance with rule chapter 74-2, F.A.C. |
|  | 4 | 3 | 2 | 1 |
| Requirements Traceability Matrix (RTM) | Required ‒ Review and amend the RTM to capture progressive detail of requirements linkage throughout the project. This matrix is used to document and link requirements from their origin to the deliverables that satisfy them. | Required ‒ Update requirements documentation as necessary. |
|  | 4 | 3 | 2 | 1 |
| Lessons Learned | Required ‒ Capture lessons learned from project team and stakeholders throughout the project. |

(4) The Agency will report project status based on the project’s R&C Category at least monthly. Form AST-F-0505B, Project Status Report (07/16), is hereby incorporated by reference in this rule. Form AST-F-0505B can be found at https://www.flrules.org/Gateway/reference.asp?No=Ref-07222. Status reports will include:

| PROJECT STATUS REPORT – Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Section 1 – Project Status Overview | A. Overview of Project Progress. |
|  | B. Overall Status |
|  | C. Schedule Performance Index (SPI) Cost Performance Index (CPI) | Not Required |
|  | 4 | 3 | 2 | 1 |
| Section 2 – Project Progress | A. Project Milestones, Deliverables & Major Tasks | Not Required |
|  | B. Scope Changes | Summarize in Section 1B Only |
|  | 4 | 3 | 2 | 1 |
| Section 3 – Project Issues and Risks | A. Project Issues | Summarize in Section 1B Only |
|  | B. Project Risks | Summarize in Section 1B Only |
|  | 4 | 3 | 2 | 1 |
| Section 4 – Project Spending Plan | A. Identify Baselined Planned Expenditures vs. Actual Expenditures | Not Required |
|  | B. Major Project Expenditures | Not Required |
|  | Attach current project spend plan | Not Required |

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.007 Closeout.

(1) The Agency must perform Project Closeout phase activities after the defined project objectives have been met and the Agency has accepted the project’s product in accordance with their deliverable acceptance criteria and governance process.

(2) The following matrix lists the closeout activities and documents required for the project based on its Risk and Complexity (R&C) Category.

(3) Specific document templates are not prescribed – any project documentation that contains the information specified in the requirements below is acceptable.

| CLOSEOUT PHASE – Requirements by Risk & Complexity Category |
| --- |
|  | 4 | 3 | 2 | 1 |
| Project Closeout Report (PCR) | Required ‒ Document the project’s accomplishments against the project budget, scope, schedule, and performance baselines. Include a discussion of the lessons learned compiled by the project team and stakeholders. The PCR must be completed as defined in the project schedule. | Required ‒ Document the project’s accomplishments against the project budget, scope, and schedule. Include a discussion of the lessons learned. |
|  | 4 | 3 | 2 | 1 |
| Post Implementation Review (PIR) Report | Required – Document whether the products or services delivered by the project meet the Agency’s business objectives, and provide the expected results and benefits as documented in the Initiation and Planning phases. Validate the cost benefit analysis and projected return on investment analysis. This analysis should be performed six months to one year after the product or service has been implemented. | Not Required |

(4) The Agency must archive all Agency and third-party project documentation or artifacts.

(5) The Agency will ensure that system operations are transitioned to the appropriate support and operational entities in conformance with the Operations and Maintenance Plan.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.

## 74-1.008 Compliance with the Florida Information Technology Project Management and Oversight Standards.

(1) Agencies as defined in rule 74-1.001, F.A.C., must comply with the Florida Information Technology Project Management and Oversight Standards.

(2) The Florida Information Technology Project Management Standards set forth in rules 74-1.001 through 74-1.008, F.A.C. will be applied to existing Agency information technology projects based on their current project management lifecycle phase as of July 1, 2015.

(a) Projects that have not been approved for Initiation by the Agency must implement all sections of the standards set forth in this rule.

(b) Projects that are in the Planning phase will undergo a Planning Gate Risk and Complexity Assessment upon completion of their detailed plans and will be subject to the project management control requirements of the standards authorized in this rule from that point. (See rules 74-1.002, F.A.C. ‒ Risk and Complexity Assessment, and 74-1.004, F.A.C. – Planning)

(c) Projects that are in the Execution phase will continue to operate under the specific Agency’s project management procedures, unless a significant Change Request is submitted (see rule 74-1.006 F.A.C. for the monitoring and controlling requirements for project change).

(3) AST will annually assess State Agency compliance with the standards set forth in this rule pursuant to section 282.0051(10), F.S.

(a) AST will assess compliance with the standards set forth in this rule via assessments of a subset of the State Agency’s IT projects.

(b) The State Agency will provide the documentation or other artifacts required by the standards set forth in this rule for AST assessment.

(c) AST will provide results of this compliance assessment to the State Agency, the Executive Office of the Governor, the President of the Senate, and the Speaker of the House.

(4) Agencies may request a variance or waiver from compliance with the standards set forth in this rule as defined in section 120.542, F.S.

(5) State Agencies receiving a variance or waiver pursuant to section 120.542, F.S., are subject to the compliance assessment process described in subsection (3), above.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.

## 74-1.009 Agency for State Technology (AST) Oversight.

(1) Section 282.0051(4), F.S., requires AST oversight on State Agency information technology projects that have total project costs of $10 million or more and that are funded in the General Appropriations Act or any other law.

(2) Section 282.0051(15), F.S., requires AST oversight on Cabinet Agency information technology projects with a total project cost of $25 million or more and that impacts one or more other agencies. Cabinet Agencies must adopt the standards contained in rules 74-1.001 through 74-1.008, F.A.C., for IT projects that have a total cost of $25 million or more and that impact one or more other agencies.

(3) Agencies will participate and assist AST in oversight of a project as follows:

(a) The Agency will provide access to all required documentation as defined within this rule to AST upon initiation of AST oversight.

(b) AST will assess schedule, cost, and scope variance based on the defined, documented, and approved Project Management Plan, budget, and the baselined schedule and spending plan.

(c) The Agency will update the project schedule weekly and provide the updated schedule to AST. AST will review the project schedule weekly and will identify and track trends in Schedule Performance Index and Cost Performance Index.

(d) The Agency will update project documentation (schedule, spend plan, scope, risk and issues) at the end of each month and provide these documents to AST no later than the 10th day of the following month.

(4) AST will review and document the project’s progress on a monthly basis. The purpose of the review is to determine trends in schedule, cost, and scope variances, (using the approved project management plan along with other project documentation) and assess project management practices. AST will further examine projects trending out of variance, review its findings with the Agency, and, if necessary, make recommendations for corrective action(s).

(5) AST will report quarterly to the Executive Office of the Governor, the President of the Senate, and the Speaker of the House of Representatives on any information technology project that AST identifies as high-risk due to the project exceeding acceptable variance ranges (pursuant to section 282.0051(4), F.S.). The quarterly report will follow the same process and format as the monthly review. Also the quarterly report will include a discussion of the risk assessment, including fiscal risks associated with proceeding to the next stage of the project, and a recommendation for corrective actions required, up to and including suspension or termination of the project. Agencies will review and acknowledge the quarterly report (or provide feedback or response) in writing to AST within 5 business days.

(6) Any project meeting the criteria for AST oversight must adhere to the requirements of a Risk and Complexity (R&C) Category 4 project.

(7) A PMP® Certified Project Manager is required for any project meeting the criteria for AST oversight. The PMP® Certified Project Manager shall, on behalf of the agency, lead the entire project team in the completion of the full project scope throughout the project lifecycle. This project manager must be an Agency employee or a contractor (an individual) of the Agency. The Agency project manager will serve as the primary point of contact for AST.

(8) Independent Verification and Validation (IV&V) must be employed throughout the project lifecycle for any project that meets the criteria for AST oversight. The Agency will purchase IV&V services in compliance with section 287.056, F.S., or procure such services in a manner consistent with Florida procurement laws. The Agency will collaborate with AST when creating solicitations and contracts for IV&V services, and when identifying the amount of funding to be requested for IV&V as part of the project’s Legislative Budget Request (LBR). IV&V contract deliverables, including invoices, will be provided to AST at or around the time they are delivered by the IV&V vendor to the Agency.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15, Amended 8-1-16.