74-1.005 Execution.

(1) The Execution phase involves carrying out and managing all the activities described in the Project Management Plan.

(2) The majority of Execution phase activities and documentation will be associated with the Agency’s specific Systems Development Life Cycle (SDLC) process and requirements.

(3) All changes to the approved and baselined Project Management Plan (project schedule, cost, or scope) must follow the Agency’s project change control and governance processes.

| EXECUTION PHASE | Risk & Complexity Category |
| --- | --- |
| Documentation or Activity | Requirements | 4 | 3 | 2 | 1 |
| Project Schedule | Execute and update the approved project schedule with actual work effort and project progress (tasks, milestones, and deliverables completed) to track Schedule Performance Index (SPI) and Cost Performance Index (CPI). | Required The Agency will update the schedule weekly. | Required The Agency will update the schedule weekly. | Execute and update the project schedule with actual work effort and project progress (tasks, milestones, and deliverables completed) weekly. | Execute and update the project schedule to track actual work effort and project progress (tasks, milestones, and deliverables completed) bi-weekly. |
| Project Spending Plan | Maintain the Project Spending Plan and include Spending Plan data in the Monthly Project Status Report (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for status report requirements.). | Required | Required | Not Required | Not Required |
| Procurement Management Plan | If procurement is required, the Agency will conduct procurements as documented in the approved Procurement Management Plan. | Required | Required | Required | Conduct procurements as documented in the Project Plan Summary. |
| Quality Management Plan | Perform quality assurance activities as specified in the approved Quality Management Plan. | Required | Required | Perform quality assurance activities outlined in the Project Plan Summary. | Perform quality assurance activities outlined in the Project Plan Summary. |
| Communications Plan | Manage project communications as specified in the approved Communications Plan. | Required | Required | Required | Manage communications and stakeholder needs as outlined in the Project Plan Summary. |
|  | Provide project status reports as required in this Rule. (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for status report requirements.) Facilitate communications within the project team and with the project sponsor and stakeholders. | Required | Required | Required | Required |
| Deliverable Acceptance Plan | Execute the Deliverable Acceptance Plan. | Required | Required | Required | Document deliverable acceptance in accordance with deliverable acceptance processes, criteria, and the project governance process outlined in the Project Plan Summary. |
| Organizational Change Management Plan | Execute the Organizational Change Management Plan. | Required | Required | Facilitate organizational change management as outlined in the Project Plan Summary. | Facilitate organizational change management as outlined in the Plan Summary. |
| Operations and Maintenance (O&M) Plan | Develop an O&M Plan prior to the scheduled completion of the project’s Execution phase. Obtain concurrence from financial, information technology, and operational managers on their readiness to support the system from a budgetary, staffing, technology, and operational perspective after go-live. | Required | Required | Required | Required |

(4) Agency project management activities required during the Execution phase are further described in Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.