74-1.009 Agency for State Technology (AST) Oversight.

(1) Section 282.0051(4), F.S., requires AST oversight on State Agency information technology projects that have total project costs of $10 million or more and that are funded in the General Appropriations Act or any other law.

(2) Section 282.0051(15), F.S., requires AST oversight on Cabinet Agency information technology projects with a total project cost of $25 million or more and that impacts one or more other agencies. Cabinet Agencies must adopt the standards contained in Rules 74-1.001 through 74-1.008, F.A.C., for IT projects that have a total cost of $25 million or more and that impact one or more other agencies.

(3) Agencies will participate and assist AST in oversight of a project as follows:

(a) The Agency and AST will cooperate to establish agreed-upon project oversight parameters (including schedule, cost, and scope) that will serve as the basis against which all project variances will be measured.

1. The project oversight parameters must be reviewed and approved by the Agency Project Sponsor (or designee), the Agency Project Manager, and the AST Project Assurance Manager within 15 business days of the beginning of AST project oversight.

2. The project oversight parameters may be revised during the life of the project based upon completion of the Agency’s formal change control and governance process. Revision to the parameters must be reviewed and approved by the Agency Project Sponsor (or designee), the Agency Project Manager, and the AST Project Assurance Manager.

(b) The Agency will provide the project’s Risk Management Plan to AST within 15 business days of the approval of the project oversight parameters. AST will review the plan and provide comment(s) to the Agency within 15 business days.

(c) The Agency will update the project schedule weekly and provide the updated schedule to AST. AST will review the project schedule weekly and will identify and track trends in Schedule Performance Index and Cost Performance Index.

(d) The Agency will update project documentation (schedule, spend plan, scope, risk and issues) at the end of each month and provide these documents to AST no later than the 10th day of the following month.

(e) AST will review and document the project’s progress on a monthly basis. The purpose of the review is to determine schedule, cost, and scope variances, (using the project oversight parameters along with other project baseline and actual documentation) and assess project risk and issues.

1. If the monthly review indicates that the project exceeds acceptable variance ranges (see Rule 74-1.006, F.A.C. ‒Monitoring and Controlling for definition of acceptable variance ranges.) in schedule, cost, or scope, AST will perform a diagnostic risk assessment, which will result in preliminary findings and recommendations for project corrective action.

2. The Agency will respond in writing to AST’s findings and recommendations within 5 business days of receipt of the findings. This response will include a corrective action plan for bringing the project back within acceptable variance ranges.

3. AST will review the preliminary findings, recommendations, and corrective action plan with the Agency.

4. AST will finalize the monthly review document (including a summary of the risk assessment, recommendations and the corrective action plan) for review by the Agency and AST management.

(4) AST will report quarterly to the Executive Office of the Governor, the President of the Senate, and the Speaker of the House of Representatives on any information technology project that AST identifies as high-risk due to the project exceeding acceptable variance ranges (pursuant to Section 282.0051(4), F.S.). Following the same process as the monthly review described in paragraph (3)(e) above, the quarterly report will include a discussion of the risk assessment, including fiscal risks associated with proceeding to the next stage of the project, and a recommendation for corrective actions required, up to and including suspension or termination of the project.

(5) Any project meeting the criteria for AST oversight must adhere to the requirements of a Risk and Complexity (R&C) Category 4 project.

(6) The Agency must use a PMP® Certified Project Manager for any project meeting the criteria for AST oversight. If the Agency designates a PMP® Certified third party or vendor project manager, the Agency must also designate an Agency employee in a Project Manager role that is ultimately responsible for the execution of the project effort and that serves as the primary point of contact for AST.

(7) Independent Verification and Validation (IV&V) must be employed for any project that meets the criteria for AST oversight. The Agency will purchase IV&V services in compliance with Section 287.056, F.S., or procure such services in a manner consistent with Florida procurement laws. The Agency will collaborate with AST when creating solicitations and contracts for IV&V services, and when identifying the amount of funding to be requested for IV&V as part of the project’s Legislative Budget Request (LBR). IV&V contract deliverables, including invoices, will be provided to AST at or around the time they are delivered by the IV&V vendor to the Agency.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.